## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Girish | 2025-10-22 | Missing values in Azure dataset causing NaN errors | Sprint 1 | Vaishnavi K | Logical | Implemented interpolation and mean imputation | 2025-10-22 | Closed | Dataset cleaned successfully
2 | Vaishnavi S | 2025-11-03 | ARIMA model failed due to non-stationary data | Sprint 2 | Yash B | Model Issue | Applied differencing and log transformation | 2025-11-04 | Closed | Model trained successfully
3 | Jaya A | 2025-11-18 | API endpoint returning 500 error | Sprint 3 | Vaishnvi S | Backend Bug | Fixed incorrect JSON serialization in Flask route | 2025-11-19 | Closed | API working fine post-fix
4 | Himanshu M | 2025-11-20 | Graph not updating after selecting a new region | Sprint 3 | Chidvilas Reddy | Frontend Logic | Added async API call and setState handler | 2025-11-20 | Closed | Dashboard is responsive
5 | Ritvik V | 2025-12-02 | Forecast data mismatch between backend/frontend | Sprint 4 | Jaya A | Integration Issue | Unified timestamp formats and re-tested | 2025-12-03 | Closed | Data alignment verified
6 | Chidvilas Reddy | 2025-12-05 | Dashboard takes long to load due to large data size | Sprint 4 | Kavati S | Performance | Optimized backend queries and payload size | 2025-12-06 | Closed | Load time improved by 60%
7 | Kavati S | 2025-12-05 | Chart.js tooltip showing wrong date labels | Sprint 4 | Himanshu M | UI Bug | Updated Chart.js configuration | 2025-12-06 | Closed | Tooltip labels are now accurate
8 | Vaishnavi K | 2025-12-06 | Minor rounding errors in CPU forecast output | Sprint 4 | Yash B | Model Output | Applied rounding logic in backend model output | 2025-12-07 | Closed | Predictions display correctly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others